## Overview
Overview
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
| Theme | [10 empty] | RIBA Stage |  | Well-being Goals
| Procedures / Strategy | Finance | Community / Users | Materials | Transport / Infrastructure | Energy | Water | Waste | Pollution | Ecology / Landscaping | Climate Change | No. | Description | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales
| 3 | 2 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 0 | Strategic Definition | 15 | 14 | 7 | 8 | 7 | 6 | 15
| 6 | 2 | 2 | 4 | 4 | 6 | 2 | 1 | 0 | 5 | 0 | 1 | Preparation and Brief | 23 | 22 | 11 | 15 | 7 | 6 | 23
| 1 | 1 | 2 | 5 | 3 | 6 | 1 | 1 | 2 | 1 | 2 | 2 | Concept Design | 18 | 18 | 18 | 9 | 6 | 5 | 18
| 5 | 2 | 1 | 4 | 1 | 6 | 1 | 1 | 2 | 1 | 1 | 3 | Developed Design | 20 | 18 | 11 | 13 | 8 | 3 | 19
| 7 | 1 | 3 | 1 | 0 | 7 | 2 | 1 | 2 | 1 | 0 | 4 | Technical Design | 16 | 16 | 13 | 14 | 6 | 3 | 17
| 3 | 7 | 5 | 2 | 1 | 0 | 1 | 3 | 1 | 1 | 0 | 5 | Construction | 20 | 12 | 12 | 12 | 5 | 4 | 13
| 4 | 1 | 2 | 1 | 2 | 3 | 1 | 1 | 0 | 1 | 1 | 6 | Handover and Close Out | 14 | 12 | 10 | 12 | 5 | 4 | 12
| 1 | 3 | 5 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 7 | In Use | 16 | 12 | 7 | 12 | 7 | 7 | 13
| 6 | 4 | 2 | 6 | 2 | 0 | 0 | 2 | 1 | 2 | 0 | 8 | End of Life | 25 | 7 | 2 | 0 | 1 | 1 | 8
Theme Total = | 36 | 23 | 25 | 26 | 15 | 31 | 10 | 12 | 11 | 16 | 8 |  | Goals Total = | 167 | 131 | 91 | 95 | 52 | 39 | 138

## RIBA 0
RIBA Stage - 0 - Strategic Definition
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals | [6 empty] | Evidence
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
Right project / location for a school | Strategic case outlining options with costs/risks/benefits | Pupil projections, building condition surveys | Client | X | X | X | X | X | X | X
PM to think of act at each area within RIBA stages | Goals workshop | Completed workshop spreadsheet | Client | X | X | X | X | X | X | X
Review feedback from previous projects | Lessons learnt document | Document | Client / (G)SL Lead
Finance
Consideration to capital, life cycle, and maintenance costs (technology / materials - CO2 / recycle etc) | OBC | Report | Client | X | X |  |  |  |  | X
Consider using Social Profit Calculator to predict social value (GVA and wellbeing factors of school employees / pupils / community users) | Social Profit Calculator | Calculator | Client | X |  |  |  | X | X
Community / Users
Stakeholders consulted on proposal | Engagement sessions | Confirmatory emails / minutes | Client |  |  |  | X | X | X | X
Identify community initiatives / supply chain for community benefits to work with during programme | Engagement sessions | Completed workshop | Client | X |  |  | X | X
Consider what kind of community facilities would be beneficial for area (e.g. WI / baby massage / gardening club / social enterprise space / community café etc) | Engagement sessions | Completed workshop | Client | X |  | X | X | X | X
Materials
Consider alternative methods of design and materials for efficiency (e.g. MMC) | Strategic document | Report | Client | X | X |  |  |  |  | X
Consider lifespan and impact of components (e.g. longer life - circular / shorter life - reusable + recyclable) | Assessments | Report | Client | X | X |  |  |  |  | X
Transport / Infrastructure
Research whether sustainable transport measures available in area | Travel Plan | Workshop / report | Client |  | X | X | X |  |  | X
Energy
Consideration to capital, life cycle, and maintenance costs - previous projects | Lessons learnt document | Document | Client | X | X |  |  |  |  | X
Water
Consideration to capital, life cycle, and maintenance costs - previous projects | Lessons learnt document | Document | Client | X | X |  |  |  |  | X
Waste
Consideration to previous projects to set targets | Lessons learnt document | Document | Client | X | X |  |  |  |  | X
Pollution
Consideration to previous projects to set targets | Lessons learnt document | Document | Client | X | X |  |  |  |  | X
Ecology / Landscaping
Consideration to previous projects to set targets | Lessons learnt document | Document | Client | X | X |  |  |  |  | X
Consider priority habitats within region (to protect if identified on site) | Surveys | Workshop / report | Client |  | X | X | X | X | X | X
Climate Change
Plan carbon offsetting methods (e.g. tree planting) | Surveys / examine best practice / calculate estimate emissions | Workshop / report | Client | X | X | X | X |  |  | X
Consider whether 'zero carbon' will be aim of project and if so define methodology | Strategy | Workshop / report | Client | X | X | X |  |  |  | X
| Theme Total = |  | Goals Total = | 15 | 14 | 7 | 8 | 7 | 6 | 15
Procedures / Strategy | 3
Finance | 2
Community / Users | 3
Materials | 2
Transport / Infrastructure | 1
Energy | 1
Water | 1
Waste | 1
Pollution | 1
Ecology / Landscaping | 2
Climate Change | 2

## RIBA 1
RIBA Stage - 1 - Preparation and Brief
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals | [6 empty] | Evidence
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
Sustainability Champion appointed: - need to determine who this Champion is and their responsibility within the project. | Business case | Appointment of Sustainability Champion is noted and minutes of reviews they convene held. | Client | X | X | X |  |  |  | X
Sustainability Champion set targets | Sustainability targets report | Report | Client | X | X |  |  |  |  | X
Project delivery stakeholders meet to identify roles / responsibilities / contributions | Engagement event | Confirmatory emails / minutes | Client |  |  |  | X | X | X
Security specialist appointed | Appoint | Contract | Design Team | X |  |  |  | X
Security specialist complete Security Needs Assessment and set recommendations | SNA | Document | Design Team | X |  |  |  | X
Set up sustainable procurement plan | Procurement strategy | Document | Client | X |  |  | X |  |  | X
Finance
Identify local spend potential (client / consultant) | Community benefits strategy | Document | Design Team | X |  |  | X | X |  | X
Fair Payment | Public Bank Account | Confirmatory emails / documents | Client | X |  |  | X
Community / Users
Identify opportunities to work with local organisations / supply chain on CBs | Engagement sessions | Confirmatory emails / minutes | Design Team | X | X |  | X |  |  | X
Third party stakeholders consulted by party independent of design process | Engagement sessions | Confirmatory emails / minutes | Design Team |  |  |  | X | X | X
Materials
Identify and evaluate appropriate materials for local vernacular / resources | Assessment and plan for material availability in region | Workshop / report | Design Team | X | X | X |  |  | X
Set material carbon targets achievable within project (e.g. Low or Zero) | Procurement strategy | Document | Design Team | X | X |  |  |  |  | X
Plan new building with deconstruction and reuse/recycling of materials in mind | CDM principal designer | Design options | Design Team | X | X |  |  |  |  | X
Consider circular economy potential of materials: - where possible use recycled materials (insulation newspapers / jeans etc) in construction and identify which materials from deconstruction of existing building/s can be reused/recycled | Procurement strategy | Document | Design Team | X | X |  |  |  |  | X
Transport / Infrastructure
Consider active transport potential in design | Travel plan | Document | Design Team |  | X | X | X |  |  | X
Transport assessment / plan (e.g. opportunity to use a community transport scheme) | Travel plan | Document | Design Team | X |  |  | X | X |  | X
Proximity to local services (shops / medical etc) | Travel plan | Walking distance mapping | Design Team | X |  |  | X | X | X
Local infrastructure for waste, water and energy considered (inc. heat networks, partners) | Sustainability plan | Site plan indiciating opportunities developed by design team for review (e.g. identifying renewable or district energy opportunities) | Design Team | X | X |  |  |  |  | X
Energy
Minimise fossil fuels needed for electricity | Energy targets | Document | Design Team | X | X | X | X |  |  | X
Minimise fossil fuels needed for heat | Energy targets | Document | Design Team | X | X | X | X |  |  | X
Identify energy storage potential | Stage 1 report | Document | Design Team
Decarbonisation strategy determined | Target (% improvement determined). Strategy on-site / off-site | Strategy documented, signed and agreed by client team and project team. | Client | X | X | X | X |  |  | X
Set key performance targets | EPC rating A or for refurbishment pledge to secure a DEC rating of C | Pledge agreed and signed by client and project teams. | Client | X | X | X | X |  |  | X
If refurb - review of current provision and identify efficiencies to be incorporated in extension / refurbishment | Desk Study | Arch & MEP desk study of energy efficiency / sustainability opportunities | Design Team | X | X | X | X |  |  | X
Water
Sustainable Urban Drainage proposal | SUDs planning | Submissions to SABs, consultation documents and meeting minutes. | Design Team |  | X | X |  |  |  | X
Water in use | Target consumption to be agreed | Design statement of intent. | Design Team |  | X |  |  |  |  | X
Waste
Identify and evaluate facilities in future building for operational recyclable waste | SUDs planning | Submissions to SABs, consultation documents and meeting minutes. | Design Team | X | X |  |  |  |  | X
Ecology / Landscaping
Strategy to minimise negative impacts upon ecosystem during preparation and construction (wildlife / soil / water etc) | Strategy work from principle: avoid -> mitigate -> compensate -> enhance -> manage | Document | Design Team |  | X |  |  |  |  | X
Identify ways to enhance ecosystem provision in final product | Desk Research | Document | Design Team |  | X | X | X |  |  | X
Ecologist appointed | Appoint | Contract | Client | X | X
Ecologist site visit and recommendations to enhance ecology | Ecology Report | Ecology Report | Design Team |  | X | X |  |  | X | X
Local biodiversity expertise sought | Identify species of local biodiversity importance | Ecology Report | Client | X | X |  |  |  | X | X
| Theme Total = |  | Total = | 23 | 22 | 11 | 15 | 7 | 6 | 23
Procedures / Strategy | 6
Finance | 2
Community / Users | 2
Materials | 4
Transport / Infrastructure | 4
Energy | 6
Water | 2
Waste | 1
Pollution | 0
Ecology / Landscaping | 5
Climate Change | 0

## RIBA 2
RIBA Stage - 2 - Concept Design
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals | [6 empty] | Evidence
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
Safe access | Health & Safety strategy developed | Stage 2 report | Design team |  |  | X |  | X
Finance
Cosider life cycle costings of materials / elements including maintenance (capital vs operational assessment) | LCC Report (Elemental) | Report | Design team | X | X |  | X |  |  | X
Community / Users
School stakeholders consulted on design | Engagement session | Confirmatory emails / minutes | Client |  |  |  | X | X | X
Material efficiency consultation with stakeholders | Engagement session | Confirmatory emails / minutes | Client | X | X |  | X
Materials
Identify and evaluate potential use of low or zero carbon materials / construction | Stage 2 report | Report | Design Team | X | X | X |  |  | X | X
Identify and evaluate supply chain for materials (transport / extraction / manufacture) | Procurement strategy | Document | Design Team | X | X | X |  |  | X | X
Identify and evaluate use of low or zero plastic materials / construction | Procurement strategy | Document | Design Team | X | X | X |  |  |  | X
Identify and evaluate use of low or zero waste materials / construction (inc. MMC - off-site but local / standard sizes in design to avoid on-site waste) | Procurement strategy | Document | Design Team | X | X | X |  |  |  | X
Identify and evaluate portential design for reuse / deconstruction | Stage 2 report | Report | Design Team | X | X | X |  |  |  | X
Transport / Infrastructure
Public transport accessibility | Travel plan | Document | Design team | X | X | X | X | X |  | X
Proximity to amenities | Travel plan | Document | Design team | X |  |  | X | X | X
Set out transport plan/measures | Travel plan | Document | Design team | X |  | X |  | X |  | X
Energy
Identify and evaluate energy storage opportunities (possible need to increase plant size) | Stage 2 report | Report | Design team | X
Visual Comfort considered (daylighting / view out) | Stage 2 report | Report | Design team |  |  | X | X
Thermal Comfort modelling | Modelling | Report | Design team |  |  | X | X
Identify passive design solutions | Minimum % reduction in predicted building energy demand | Report | Design team | X | X | X |  |  |  | X
Analysis of free cooling solutions | Modelling | Report | Design team | X | X | X |  |  |  | X
Feasability of local low or zero carbon energy sources | Minimum % reduction in CO2 emissions | Report | Client | X | X | X |  |  |  | X
Water
Flood risk and surface water run off potential considered | SUDS | SAB approval | Design team | X | X | X | X |  |  | X
Waste
Pre-deconstruction audit of construction waste management (on-site construction of new build / deconstruction of any existing buildings) | Procurement strategy | Document | Design team | X | X | X |  |  |  | X
Pollution
Minimising sources of air pollution (building ventilation / site selection) | Air pollution strategy | Document | Design team |  | X | X |  |  |  | X
Consider availability of previously developed land and contaminated land | Strategic case | Document | Client |  | X |  |  |  |  | X
Ecology / Landscaping
Space for nature' embedded within design (reflect local needs / priorities) | Landscape strategy | Document | Client |  | X | X | X | X | X | X
Climate Change
Climate change adaptation strategy appraisal for structural and fabric resilience | Risk assessment and modelling | Risk assessment and modelling | Design Team | X | X | X |  |  |  | X
Building specific functional adaptation strategy | Recommendations to facilitate adaptation | Document | Design Team | X | X |  |  |  |  | X
| Theme Total = |  | Total = | 18 | 18 | 18 | 9 | 6 | 5 | 18
Procedures / Strategy | 1
Finance | 1
Community / Users | 2
Materials | 5
Transport / Infrastructure | 3
Energy | 6
Water | 1
Waste | 1
Pollution | 2
Ecology / Landscaping | 1
Climate Change | 2

## RIBA 3
RIBA Stage - 3 - Developed Design
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
PAC process | Consultation/ drawing and reports | Consultation | Contractor | X |  |  | X | X | X | X
BIM modelling | NWD / IFC files | Model file | Design team / Contractor | X | X
Building Regulations Part L assessment | Building control review | Sign off from building control | Design team / Contractor
Review sustainable procurement plan | QS review | Sign off from QS | Client | X |  |  | X
Review procedures for H&S, secuirity, safe and healthy surroundings | CDM principal designer review | Sign off from CDM principal designer | Contractor |  |  | X | X | X
Finance
Life cycle costings of materials appraised | LCC Report (whole cost) | Report | Contractor | X | X |  |  |  |  | X
Cost appraisal 'Welsh pound' | % spend within Wales target | Cost Plan / CSA Report | Contractor | X |  |  | X |  |  | X
Community / Users
School stakeholders consulted on design and have access to decision makers | Weekly / monthly engagement sessions | Confirmatory emails / minutes | Client |  |  |  | X | X | X
Materials
Development and implementation of materials strategy (efficiencies) | Specification / schedules | Spec and eg WRAS | MEP / Contractor | X | X |  |  |  |  | X
Material selection on the BRE green guide rating | RIBA spec | Spec/drawings | Architect | X | X |  | X |  |  | X
Material efficiency consultation with stakeholders | Engagement session | Confirmatory emails / minutes | Design Team | X | X |  | X
Design for disassembly and adaptability embedded | End user guide | Document | Design Team | X | X | X | X |  |  | X
Transport / Infrastructure
Set out transport plan/measures | Travel plan | Document | Design team | X |  | X |  | X |  | X
Energy
Low or zero carbon renewables selected | Specification | Report | Design Team | X | X | X |  |  |  | X
Minimise fossil fuels needed for electricity | Test design against modelling assumptions, deploy suitable renewable technology | Report | Design Team | X | X | X | X |  |  | X
Minimise fossil fuels needed for heat | Test design against modelling assumptions, deploy suitable renewable technology | Report | Design Team | X | X | X | X |  |  | X
Decarbonisation strategy integrated into design | Design complies with targets set | Decarbonisation targets monitored as design progresses | Client / Contractor / Design Team | X | X | X | X |  |  | X
Key performance targets set | TM54 workshop | Results of TM54 workshop and analysis | Client / Contractor / Design Team | X | X | X | X |  |  | X
Development and implementation of energy strategy (efficiencies) | Specificaiton / schedules | Spec and eg WRAS | MEP | X | X |  |  |  |  | X
Water
Development and implementation of water strategy (efficiencies) | Specification / schedules | Spec and eg WRAS | MEP | X | X |  |  |  |  | X
Waste
Development and implementation of waste strategy (efficiencies) | Specification / schedules | Spec and eg WRAS | MEP / Contractor | X | X |  |  |  |  | X
Pollution
Design to embed considerations to reduce night time light pollution | Specification / schedules | Spec/drawings | Design Team | X | X |  |  | X |  | X
Design to embed considerations to achieve satisfactory indoor air quality and acoustic performance | Specification / schedules | Spec/drawings | Design Team |  | X | X |  | X |  | X
Ecology / Landscaping
Development and implementation of ecology strategy (focus on maximising positive opportunities and minimising damage) | Specification / schedules | Report | Design Team |  | X | X | X | X | X | X
Climate Change
Environmental standards set | Specification / schedules | Report | Client | X | X | X |  | X |  | X
| Theme Total = |  | Total = | 20 | 18 | 11 | 13 | 8 | 3 | 19
Procedures / Strategy | 5
Finance | 2
Community / Users | 1
Materials | 4
Transport / Infrastructure | 1
Energy | 6
Water | 1
Waste | 1
Pollution | 2
Ecology / Landscaping | 1
Climate Change | 1

## RIBA 4
RIBA Stage - 4 - Technical Design
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals
Objectives | Metric | Type | Metric | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
Healthy engagement with planning department to understand wider priorities | Engagement session | Confirmatory emails / minutes | Contractor / Planning Consultant | X |  |  | X
WELL Building standard - performance based system, measuring features of the built environment impact human health and well being. | WELL Building Standards | Standard | Contractor / Design team | X |  | X |  | X |  | X
Construction and H&S strategy | PD Assesments / H&S Plans | Report / assessment | Contractor | X | X | X | X |  |  | X
Compliance and evidencing in design and construction | Design / Installation | Drawings and Building Control sign off/reporting | Contractor |  | X |  | X |  |  | X
Third party submission (fire regulations) | Fire Officer review | Confirmatory emails / minutes | SWFS | X | [5 empty] | X
Part L Doc (EPC / air tightness / thermal mass / renewables) | Submission to Building Control | Report | Design team / Contractor |  |  | X | X
Secure by Design | Police review | Confirmatory emails / minutes |  |  |  |  | X | X | X
Finance
Life cycle costings of materials accounted for in decisions | LCC Report (component) | Document | Contractor | X | X |  |  |  |  | X
Community / Users
Specialist sub contractor/consultants engaged to review implementations on acoustics/lighting/sports provisions | Consultant review / recommendations | Reports / design review minutes | Contractor / Design team |  |  | X |  | X
School stakeholders consulted on design | Weekly / monthly engagement sessions | Confirmatory emails / minutes | Client |  |  |  | X | X | X
Material efficiency consultation with stakeholders | Engagement session | Confirmatory emails / minutes | Client | X | X |  | X
Materials
Development and implementation of materials strategy (efficiencies) | Specification / schedules | Spec and eg WRAS | MEP | X | X |  |  |  |  | X
Transport / Infrastructure
Energy
Development and implementation of energy strategy (efficiencies) | Specification / schedules | Spec and eg WRAS | MEP | X | X |  |  |  |  | X
Minimise fossil fuels needed for electricity | Test design against modelling assumptions, deploy suitable renewable technology | Model | Design Team | X | X | X | X |  |  | X
Minimise fossil fuels needed for heat | Test design against modelling assumptions, deploy suitable renewable technology | Model | Design Team | X | X | X | X |  |  | X
Decarbonisation strategy integrated into design | Design complies with targets set | Decarbonisation targets monitored as design progresses | Design Team | X | X | X | X |  |  | X
Key performance targets | TM54 workshop held | Results of TM54 workshop and analysis | Design Team | X | X | X | X |  |  | X
Visual Comfort embedded (daylighting / view out) | Design drawing | Drawing | Design team |  |  | X | X
Thermal Comfort embedded | Design drawing | Drawing | Design team |  |  | X | X
Water
Development and implementation of water strategy (efficiencies) | Specification / schedules | Spec and eg WRAS | MEP | X | X |  |  |  |  | X
Development and implementation of SUDs | Specification / schedules | SAB approval | Design team | X | X |  |  |  |  | X
Waste
Development and implementation of waste strategy (efficiencies) | Specification / schedules | Spec and eg WRAS | MEP | X | X |  |  |  |  | X
Pollution
Design to embed considerations to achieve satisfactory indoor air quality and acoustic performance | Specification / schedules | Report | Design team |  | X | X |  | X |  | X
Develop on-site pollution mitigation strategy | Strategy developed | Report (list of mitigation / control measures) | Contractor | X | X | X |  |  |  | X
Ecology / Landscaping
Space for Nature embedded in design | Landscape drawing | Drawing | Design team |  | X | X | X | X | X | X
| Theme Total = |  | Total = | 16 | 16 | 13 | 14 | 6 | 3 | 17
Procedures / Strategy | 7
Finance | 1
Community / Users | 3
Materials | 1
Transport / Infrastructure | 0
Energy | 7
Water | 2
Waste | 1
Pollution | 2
Ecology / Landscaping | 1
Climate Change | 0

## RIBA 5
RIBA Stage - 5 - Construction* |  | (*See stage 8 if demolishing existing building)
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
CLOCs | Certificate | Certificate | Contractor |  |  | X
As Constructed' information | Stage 4 report | Document | Contractor | X
Zero Defects | Maximum acceptable levels | Snagging report | Contractor | X |  |  | X |  |  | X
Finance
Jobs created (NEET / LT unemployed - sustainability of jobs) | Person weeks per £m investment | Job offer letter / confirmatory emails / professional development record | Contractor | X |  | X | X |  |  | X
Training (including graduates, work placements, pupil placement) | Person weeks of training per £m investment (included in above) | Training offer letter / confirmatory emails / professional development record | Contractor | X |  |  | X | X | X
Apprentices | Number of places provided | Apprentiship offer letter / confirmatory emails / professional development record | Contractor | X |  |  | X |  | X
Spend in Wales | % of construction value spent in Wales | Order forms / financial records | Contractor | X |  |  |  | X
Welsh subcontractors | % of subcontractors with Welsh postcode | Order forms / financial records | Contractor | X |  |  | X | X
Workforce from Wales | % of workforce with a Welsh postcode | Employee postcode details | Contractor | X |  | X | X |  |  | X
Fair Payment | PBA | Confirmatory emails / documents | Client | X |  |  | X
Community / Users
Pupil interactions / hours donated | Number of pupil interactions per £m and Number of hours donated per £m | Monitoring forms / workshop documents | Contractor | X |  |  | X | X
Community initiatives (delivered in response to needs identified in initial stages) | Number of community initiatives per project | Assistance offer letter / confirmatory emails / social media / financial record | Contractor |  | X | X | X | X
Supply chain engagements | Number of supply chain engagements per project | Monitoring forms / workshop documents | Contractor |  | X |  | X |  |  | X
Prepare building user guides and training schedules (information required for handover, asset management, future monitoring and maintenance) | Building User Guide | Document | Client / contractor | X |  |  | X |  | X
Material efficiency consultation with stakeholders | Engagement session | Confirmatory emails / minutes | Client / contractor | X | X |  | X
Materials
Minimise carbon cost of construction | Identify and implement efficiencies | EE & EC materials | Contractor | X | X | X |  |  |  | X
Installation of certified products | Green guide A / A+ | Materials list | Contractor | X | X | X |  |  |  | X
Transport / Infrastructure
Minimise carbon cost of transport to site | Identify and implement efficiencies | No. of vehicle trips / distance to site / fuel use | Contractor | X | X | X |  |  |  | X
Water
Minimise water use to and on site | Monitor consumption (BREEAM benchmark) | Meter readings | Contractor | X | X |  |  |  |  | X
Waste
Minimise on site waste through strategy implementation | CEMP | Document | Contractor | X | X | X |  |  |  | X
Minimise waste to landfill | % waste diverted from landfill | KPI document | Contractor | X | X | X |  |  |  | X
Monitor how materials / products not sent to landfill are being reused / recycled | CEMP | Document / supply chain map | Contractor | X | X | X |  |  |  | X
Pollution
Minimise pollution from site (mitigation strategy measures) | CEMP | Document | Contractor | X | X | X |  |  |  | X
Ecology / Landscaping
Implement mitigation measures to protect natural assets | Protection of all natural assets identified for perservation | Site reports | Contractor |  | X | X |  |  | X | X
| Theme Total = |  | Total = | 20 | 12 | 12 | 12 | 5 | 4 | 13
Procedures / Strategy | 3
Finance | 7
Community / Users | 5
Materials | 2
Transport / Infrastructure | 1
Energy | 0
Water | 1
Waste | 3
Pollution | 1
Ecology / Landscaping | 1
Climate Change | 0

## RIBA 6
RIBA Stage - 6 - Handover and Close Out* |  | (*See stage 8 if demolishing existing building)
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals | [6 empty] | Evidence
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
As Constructed' information updated | BIM model | Cobie, IFC, documentation | Client | X | X | X | X | X |  | X
WG toolkit | Met grant conditions | Complete online | Client / End user | X | X | X | X | X | X | X
Latent defects resolved | Snagging reported and resolved | Reports | Contractor | X |  | X | X
Evaluate success of project delivery | Review process for good practice / lessons learnt (e.g. costs, design, time, H&S) | Workshop / report | Client / Contractor |  |  |  | X
Finance
Fair Payment | PBA | Confirmatory emails / documents | Contractor | X |  |  | X
Community / Users
Material efficiency consultation with stakeholders | Workshop and guide | Confirmatory emails / minutes | Client / Contractor / End user | X | X |  | X
Building User Guide developed and distributed | Workshop and guide | Confirmatory emails / minutes | Client / Contractor / End user | X | X |  | X |  |  | X
Materials
Maintenance handover guide | Handbook | Document | Client / Contractor / End user | X | [5 empty] | X
Transport / Infrastructure
Verification of transport emissions | Construction transport emissions met conditions / targets | Report | Contractor | X | X | X |  |  |  | X
Travel plan and sustainable transport | Travel plan | Document | Client / End user | X | X | X | X |  |  | X
Energy
Key performance targets | EPC issued - submeters installed | EPC issued to client team and accepted | Contractor | X | X | X | X |  |  | X
Energy systems training and handover | Walk-about with staff, training care taker | O&M Plus additional support through snagging 12 months | Contractor | X | X | X | X |  |  | X
Achieve BREEAM | BREEAM certificate awarded | BREEAM Certification | Client / Contractor | X
Water
SUDs used as teaching resource | Building user guide | Document | Client / Contractor / End user | X | X | X | X | X | X | X
Waste
Waste management practices | Building user guide | Document | Client / Contractor / End user |  | X | X |  |  |  | X
Ecology / Landscaping
Eco committee in place / green flag status | Certificate | Certificate | End user |  | X |  |  | X | X | X
Climate Change
Climate change adaptation plan | Building user guide | Document | Client / Contractor / End user | X | X | X | X | X | X | X
| Theme Total = |  | Total = | 14 | 12 | 10 | 12 | 5 | 4 | 12
Procedures / Strategy | 4
Finance | 1
Community / Users | 2
Materials | 1
Transport / Infrastructure | 2
Energy | 3
Water | 1
Waste | 1
Pollution | 0
Ecology / Landscaping | 1
Climate Change | 1

## RIBA 7
RIBA Stage - 7 - In Use
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals | [6 empty] | Evidence
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
WG toolkit (Brighter Spaces) | Welsh Government 'Brighter Spaces' Toolkit | Complete online | Client | X | X | X | X | X | X | X
Finance
Actual maintenance cost | % reduction ongoing costs comparison with baseline | Financial reports | Client / end user | X |  |  | X
Added value of building | Lessons learnt document / 'Brighter Spaces' toolkit | Complete online | Client / contractor / FM | X
Income generation | Income covers cost of maintenance | Bookings / finance reporting | End user
Community / Users
Educational attainment | % achieving expected level | Annual results | Client | X |  |  | X | X | X
Post ocupancy survey | Pupil / staff satisfaction | Interviews / POE reports | Client / SL Champion |  |  |  | X | X | X
Community use of recreation / meeting facilities | Bookings increase / 'Brighter Spaces' toolkit | Sign in sheets / confirmatory emails | End user | X |  |  | X | X | X
Special events held (possible link with twinned schools / towns) | Bookings increase / 'Brighter Spaces' toolkit | Bookings / confirmatory emails | End user |  |  |  | X | X | X | X
Legacy of community benefits | TR&T longer term employment, longevity of wider community benefit | Surveys | Client | X |  |  | X | X | X
Materials
Maintence ongoing | Maintence requirements met | Receipts of works / monitoring forms | Client / end user | X |  |  | X
Transport / Infrastructure
Ensure transport strategy in place | Travel plan | Document | End user | X | X | X |  |  |  | X
Energy
Key performance targets met (minimise electricity and heat from fossil fuels and overall energy use) | Seasonal commissioning undertaken - sub-meters for renewables / individual rooms | Annual reports from meter readings (kWh/a) | Client / contractor | X | X | X | X |  |  | X
Training and handover | Training with end-users - making use of their feedback and behaviour change advise so operating building as design intented. | End user feedback and training | Client / end user | X | X | X | X |  |  | X
Water
Monitoring water use | Brighter Spaces' Toolkit | Complete online | Client / end user | X | X |  |  |  |  | X
Waste
Monitor use of facilities for separate recycling | Lessons learnt document | Document | Client / end user |  | X | X |  |  |  | X
Pollution
Monitoring of soil and water quality | Lessons learnt document | Document | Client / end user | X | X |  |  |  |  | X
Monitoring of air pollution (indoor and outdoor) | Lessons learnt document | Document | Client / end user | X | X |  |  |  |  | X
Ecology / Landscaping
Monitoring of biodiversity | Lessons learnt document | Document | Client / end user | X | X |  |  |  |  | X
Maintenance and use of outdoor areas | Lessons learnt document | Document | End user / FM | X | X | X | X | X | X | X
Climate Change
Monitor building resiliance to climate change | Lessons learnt document | Document | Client / end user | X | X |  | X |  |  | X
Carbon offsetting (site / borough / Wales) | % carbon from construction absorbed by tree planting | Calculate number and size of trees at milestones (10 / 25 / 50 years) against carbon cost of construction data | Client |  | X | X |  |  |  | X
| Theme Total = |  | Total = | 16 | 12 | 7 | 12 | 7 | 7 | 13
Procedures / Strategy | 1
Finance | 3
Community / Users | 5
Materials | 1
Transport / Infrastructure | 1
Energy | 2
Water | 1
Waste | 1
Pollution | 2
Ecology / Landscaping | 2
Climate Change | 2

## RIBA 8
RIBA Stage - 8 - End of Life (Current Building)
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals | [6 empty] | Evidence
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
Standardise manufacturers list across the Authority so that in decommissioning site A, plant may be deployed to sites B and C etc. | Decommissioning plan | Document | Client / contractor | X | X
Flexible design limits demo |  | Report | Client | X
Decommissioning manger appointed | Appoint | Contract | Client | X
Finance
Shell and core assets mapped | Audit of assets | Report | Client | X
Community / Users
Community use of existing asset mapped | Workshops and desk research | Report | Client | X |  |  |  | X | X | X
Materials
Maximise materials able to be reused | Tonnes of materials reused | Material logs | Contractor | X | X |  |  |  |  | X
Maximise materials able to be recycled | Tonnes of materials recycled | Material logs | Contractor | X | X |  |  |  |  | X
Monitor legacy of building / materials (aim to reuse building in first instance) | Decommissioning plan | Document | Client / contractor | X |  |  |  | X | X | X
Transport / Infrastructure
Transport analysis | Asset mapping | Report | Client | X | X | X | X |  |  | X
Waste
Conduct deconstruction survey and responsibly reuse / upcycle / dispose products and materials | Decommissioning plan | Document | Contractor | X | X | X |  |  |  | X
Pollution
Risk assessment of old building pollutants (e.g. asbestos) | Pollutant assessment | Report | Contractor | X | X | X |  |  |  | X
Ecology / Landscaping
Mitigate negative impacts upon ecology | Ecologist assessment | EIA | Client / contractor | X | X |  |  |  |  | X
| Theme Total = |  | Total = | 12 | 7 | 3 | 1 | 2 | 2 | 8
Procedures / Strategy | 3
Finance | 1
Community / Users | 1
Materials | 3
Transport / Infrastructure | 1
Energy | 0
Water | 0
Waste | 1
Pollution | 1
Ecology / Landscaping | 1
Climate Change | 0
RIBA Stage - 8 - End of Life (New Building - 60~ years)
Well-being of Future Generations (Wales) Act 2015 RIBA Directory
Area of Work |  |  |  | Well-being Goals | [6 empty] | Evidence
Objectives | Metric | Type | Responsibility | A Prosperous Wales | A Resilient Wales | A Healthier Wales | A More Equal Wales | A Wales of Cohesive Communities | A Wales of Vibrant Culture and Thriving Welsh Language | A Globally Responsible Wales | Location | Ownership
Procedures / Strategy
Standardise manufacturers list across the Authority so that in decommissioning site A, plant may be deployed to sites B and C etc. | Decommissioning plan | Document | Client / contractor | X
Flexible design limits demo |  | Report | Client | X
Decommissioning manger appointed | Appoint | Contract | Client | X
Finance
Review projected value of building in use to verify and confirm | Met expected value | Post completion assessment | Client | X
Lease kit - e.g. LED hire services (only example not TB+A recommendation, others offer similar) |  |  |  | X | X |  |  |  |  | X
Shell and core assets mapped | Audit of assets | Report | Client | X
Community / Users
Community use of existing asset mapped | Workshops and desk research | Report | Client | X |  |  |  | X | X | X
Materials
Maximise materials able to be reused | Tonnes of materials reused | Material logs | Contractor | X | X |  |  |  |  | X
Maximise materials able to be recycled | Tonnes of materials recycled | Material logs | Contractor | X | X |  |  |  |  | X
MEP - from MEP point of view by Stage 8 (anticitipated to be 60 years +) all plant is likely to have been renewed and replaced | Decommissioning plan | Document |  | X
Transport / Infrastructure
Transport analysis | Asset mapping | Report | Client | X | X | X | X |  |  | X
Waste
Conduct deconstruction survey and responsibly reuse / upcycle / dispose products and materials | Decommissioning plan | Document | Contractor | X | X | X |  |  |  | X
Pollution
Ecology / Landscaping
Mitigate negative impacts upon ecology | Ecologist assessment | EIA | Client / contractor | X | X |  |  |  |  | X
| Theme Total = |  | Total = | 13 | 6 | 2 | 1 | 1 | 1 | 7
Procedures / Strategy | 3
Finance | 3
Community / Users | 1
Materials | 3
Transport / Infrastructure | 1
Energy | 0
Water | 0
Waste | 1
Pollution | 0
Ecology / Landscaping | 1
Climate Change | 0